## Sheet1
Project 2 Group 4
Type | Priority | Description | sprint 3 | Sprint 3
Game Logic | 1 |  |  | sprint progress | Initial | Meeting 1 | Meeting 2 | Meeting 3 | Final
| 1.1 | Create Title/ Introduction to Kalah | 0 | hours left | 26 | 10 | 6 | 0 | 0
| 1.2 | Create Instructions for the game | 0
| 1.3 | Create Objects for 6 houses and 2 Kalah | 0
| 1.4 | Input 4 seeds in each house | 0
| 1.5 | Take in user input by keyboard | 0
| 1.6 | Check if move is valid or not | 0
| 1.7 | distribute seeds correctly after user input | 0
| 1.8 | display houses, seed count, and score | 0
| 1.9 | display winner, loser, or tie | 0
| 1.1 | user option to reset current game | 0
| 1.11 | Options for user to enter instructions | 0
| 1.12 | give user option to replay or quit game | 0
| 1.13 | Implement a timer for each move | 0
| 1.14 | let user undo move (optional) | 0
| 1.15 | keep track of wins and losses (optional) | 0
| 1.16 | allow random distribution of seeds | 0
| 1.17 | implement "pie rule" | 0
AI | 2
| 2.1 | Identify All valid moves | 0
| 2.2 | randomly select random valid move (minimax tree) | 0
| 2.3 | Look ahead one move in a tree | 0
| 2.4 | implement minimax tree | 0
| 2.5 | Alpha-beta pruning 1 level | 0
| 2.6 | alpha-beta pruning all level | 2
| 2.7 | Make an easy mode | 0
| 2.8 | make a medium mode | 0
| 2.9 | make a hard mode | 0
| 2.1 | board evaluation function to determine a winner or loser | 0
| 2.11 | implement utility function for AI | 3
GUI | 3
| 3.1 | draw the board | 0
| 3.2 | draw location for instructions and reset | 0
| 3.3 | show options for AI difficulty | 1
| 3.4 | take user input by clicks | 0
| 3.5 | check validity of user input | 1
| 3.6 | display amount of seeds in each house | 0
| 3.7 | display score | 0
| 3.8 | display timer | 0
Server | 4
| 4.1 | connect server to AI | 3
| 4.2 | connect server to GUI | 2
| 4.3 | create connections to clients | 2
| 4.3 | read messages from client | 2
| 4.4 | write messages to client | 2
| 4.5 | parse given information from user | 2
| 4.6 | return errors if not pared correctly | 2
| 4.7 | implement client commands in game | 3
| 4.8 | client acknowledgement | 1
|  | total hours | 26
|  | total hours left | 0